PROPOSED TIMELINE FOR

NATIONAL LATINO/HISPANIC AIDS ACTION AGENDA & SUMMIT

MAY

- Face-to-face meeting at HPLS - 5/20/07

- General Planning Conference Call - 5/30/07

JUNE

- Production & Feedback for Workgroups of Action Agenda

- General Planning Conference Call - 6/26/07

JULY

- Production & Feedback for Workgroups of Action Agenda

- General Planning Conference Call - 7/24/07

AUGUST

- Draft of National Call to Action Completed

- General Planning Conference Call - 8/28/07

SEPTEMBER

- Present National Call to Action – meet/visits with government agencies – mobilization effort begins

- Galvanize press – marketing / press effort begins / key national meetings

- General Planning Conference Call - 9/25/07

OCTOBER

- Congress Adjourns

- General Planning Conference Call - 10/30/07

NOVEMBER

- Draft Document of National Latino AIDS Action Agenda completed

- Second face-to-face meeting to review draft agenda – United States Conference on AIDS, Nov 7-10th Palm Springs, CA

- General Planning Conference Call - 11/28/07

DECEMBER

- Workgroups Review and finalize sections

- General Planning Conference Call - 12/19/07

JANUARY

- Congress reconvenes

- National Latino Agenda Summit January 29th and 30th 2008 in Washington, DC